## Sheet1
No. | Group | Task | Owner | Progress | Note
1 | Preparation | 1.1 Init github skeleton source code | Nhan | Done
|  | 1.2 Spike on email sender | Murad | Done
|  | 1.3 Design draft class diagram | Yonas | Done
|  | 1.4 Spike on integration bank ui and backend | Eden + Henock | Done
|  | 1.5 Spike on integration creditcard ui and backend | Nhan | Done
|  | 1.6 Design code structure base on the draft diagram | Yonas | Done
|  | 1.7 Split requirement on tasks | Nhan | Done
2 | Design class diagram to a bank system | Draw class diagram | Nhan + Yonas | Done
3 | Design class diagram for a creditcard processing system | Draw class diagram | Nhan + Yonas | Done
4 | Implement the Banking Application | 4.1 Backend | Yonas + Murad | Done | Yonas do the backend, Murad do the observer email sender
|  | 4.2 Fronend | Yonas + Nhan | Done | Nhan: integrate generate report Yonas: do the rest of things
5 | Implement the Credit Card Application | 5.1 Backend | Yonas + Nhan | Done
|  | 5.2 Frontend | Yonas + Nhan | Done
6 | Sequence diagrams | 6.1 Bank System | Eden | Done
|  | 6.2 CreditCard System | Henock | Done
7 | Integration and merge code | All system | Nhan | Done | Everyone are not familiar with github, then I help them to merge the code